## Workstreams
Workstream | Phase | Task ID | Task Name | Start Date | End Date | Duration (Effort Days) | Assigned To | Task Type | Activity Status | Actual % Complete | Dependencies | Dependency Type | Notes
WorkStream-1 | P1 | A1.1 | Conduct stakeholder readiness interviews (Gx, Tx, Dx, CE, D&T) | 2025-05-01 | 2025-05-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P1 | A1.2 | Synthesize urgency drivers (regulatory, reliability, efficiency) | 2025-05-04 | 2025-05-09 | 5 |  | Execution | Not Started | 0 | A1.1 | FS
WorkStream-1 | P1 | A1.3 | Define pilot risks and opportunities to reinforce urgency | 2025-05-07 | 2025-05-12 | 5 |  | Execution | Not Started | 0 | A1.2 | FS
WorkStream-1 | P1 | A1.4 | Develop AIS urgency narrative and value proposition | 2025-05-10 | 2025-05-15 | 5 |  | Execution | Not Started | 0 | A1.3 | FS
WorkStream-1 | P1 | A1.5 | Align CE, D&T and BL leadership on communication tone | 2025-05-13 | 2025-05-18 | 5 |  | Execution | Not Started | 0 | A1.4 | FS
WorkStream-1 | P1 | A1.6 | Draft awareness materials: infographics, email series | 2025-05-16 | 2025-05-21 | 5 |  | Execution | Not Started | 0 | A1.5 | FS
WorkStream-1 | P1 | A1.7 | Launch structured AIS awareness email campaign | 2025-05-19 | 2025-05-24 | 5 |  | Execution | Not Started | 0 | A1.6 | FS
WorkStream-1 | P1 | A1.8 | Quantify and communicate the business value of high-quality asset data (e.g., AHI-driven decisions, failure prevention) | 2025-05-22 | 2025-05-27 | 5 |  | Execution | Not Started | 0 | A1.7 | FS
WorkStream-1 | P1 | M1.1 | D1.1 – Change Management Plan (initial: urgency, readiness) | 2025-05-25 | 2025-05-25 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P1 | M1.2 | D1.2 – Communication Strategy (urgency narrative) | 2025-05-28 | 2025-05-28 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P1 | M1.3 | D1.3.x – Awareness Campaign Materials | 2025-05-31 | 2025-05-31 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P2 | A2.1 | Identify executive sponsors from CE, D&T, and Business Lines | 2025-06-01 | 2025-06-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P2 | A2.2 | Define roles and responsibilities of the change leadership coalition | 2025-06-04 | 2025-06-09 | 5 |  | Execution | Not Started | 0 | A2.1 | FS
WorkStream-1 | P2 | A2.3 | Set up Change Governance Committee and Working Groups | 2025-06-07 | 2025-06-12 | 5 |  | Execution | Not Started | 0 | A2.2 | FS
WorkStream-1 | P2 | A2.4 | Nominate Data Stewards and Change Agents per BL | 2025-06-10 | 2025-06-15 | 5 |  | Execution | Not Started | 0 | A2.3 | FS
WorkStream-1 | P2 | A2.5 | Conduct orientation and briefings for the coalition team | 2025-06-13 | 2025-06-18 | 5 |  | Execution | Not Started | 0 | A2.4 | FS
WorkStream-1 | P2 | A2.6 | Draft coalition mandate and engagement calendar | 2025-06-16 | 2025-06-21 | 5 |  | Execution | Not Started | 0 | A2.5 | FS
WorkStream-1 | P2 | M2.1 | Updated D1.1 (coalition roles, working groups) | 2025-06-19 | 2025-06-19 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P2 | M2.2 | D1.3.x – Orientation Materials | 2025-06-22 | 2025-06-22 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P3 | A3.1 | Facilitate CE-led visioning workshop on AIS purpose and outcomes | 2025-07-01 | 2025-07-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P3 | A3.2 | Draft AIS Vision and Change Narrative (CE/D&T endorsed) | 2025-07-04 | 2025-07-09 | 5 |  | Execution | Not Started | 0 | A3.1 | FS
WorkStream-1 | P3 | A3.3 | Define high-level change management goals and KPIs | 2025-07-07 | 2025-07-12 | 5 |  | Execution | Not Started | 0 | A3.2 | FS
WorkStream-1 | P3 | A3.4 | Map key governance roles and decision-making bodies | 2025-07-10 | 2025-07-15 | 5 |  | Execution | Not Started | 0 | A3.3 | FS
WorkStream-1 | P3 | A3.5 | Outline pilot opportunities aligned to AIS vision | 2025-07-13 | 2025-07-18 | 5 |  | Execution | Not Started | 0 | A3.4 | FS
WorkStream-1 | P3 | A3.6 | Draft and review AIS Change Management Project Charter | 2025-07-16 | 2025-07-21 | 5 |  | Execution | Not Started | 0 | A3.5 | FS
WorkStream-1 | P3 | A3.7 | Approve and publish the Project Charter | 2025-07-19 | 2025-07-24 | 5 |  | Execution | Not Started | 0 | A3.6 | FS
WorkStream-1 | P3 | M3.1 | D1.1 – Project Charter Finalized (vision, scope, governance) | 2025-07-22 | 2025-07-22 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P4 | A4.1 | Define key audience segments and communication objectives (Executives, Ops, Engineers, Data Teams) | 2025-08-01 | 2025-08-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P4 | A4.2 | Select appropriate channels and frequency (email, townhalls, briefings) | 2025-08-04 | 2025-08-09 | 5 |  | Execution | Not Started | 0 | A4.1 | FS
WorkStream-1 | P4 | A4.3 | Develop CE AIS Messaging Framework (themes, tone, common language) | 2025-08-07 | 2025-08-12 | 5 |  | Execution | Not Started | 0 | A4.2 | FS
WorkStream-1 | P4 | A4.4 | Create supporting materials (briefing decks, infographics, FAQs) | 2025-08-10 | 2025-08-15 | 5 |  | Execution | Not Started | 0 | A4.3 | FS
WorkStream-1 | P4 | A4.5 | Train CE/D&T leadership on delivering the AIS vision consistently | 2025-08-13 | 2025-08-18 | 5 |  | Execution | Not Started | 0 | A4.4 | FS
WorkStream-1 | P4 | A4.6 | Execute first wave of communications (executive briefings, campaign emails, townhalls) | 2025-08-16 | 2025-08-21 | 5 |  | Execution | Not Started | 0 | A4.5 | FS
WorkStream-1 | P4 | A4.7 | Monitor engagement and feedback from BLs | 2025-08-19 | 2025-08-24 | 5 |  | Execution | Not Started | 0 | A4.6 | FS
WorkStream-1 | P4 | M4.1 | D1.2 – Communication Strategy Final Version | 2025-08-22 | 2025-08-22 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P4 | M4.2 | D1.3.x – Exec Briefings, Webinars | 2025-08-25 | 2025-08-25 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P5 | A5.1 | Operationalize governance roles and responsibilities from Change Management Plan | 2025-09-01 | 2025-09-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P5 | A5.2 | Identify organizational or procedural barriers (resistance, unclear ownership, tool gaps) | 2025-09-04 | 2025-09-09 | 5 |  | Execution | Not Started | 0 | A5.1 | FS
WorkStream-1 | P5 | A5.3 | Develop change agent toolkit: FAQs, talking points, decision trees | 2025-09-07 | 2025-09-12 | 5 |  | Execution | Not Started | 0 | A5.2 | FS
WorkStream-1 | P5 | A5.4 | Develop and launch AIS training program – Phase 1 (awareness) | 2025-09-10 | 2025-09-15 | 5 |  | Execution | Not Started | 0 | A5.3 | FS
WorkStream-1 | P5 | A5.5 | Deliver training sessions across business lines (Gx, Tx, Dx) | 2025-09-13 | 2025-09-18 | 5 |  | Execution | Not Started | 0 | A5.4 | FS
WorkStream-1 | P5 | A5.6 | Collect feedback and adapt training/coaching support | 2025-09-16 | 2025-09-21 | 5 |  | Execution | Not Started | 0 | A5.5 | FS
WorkStream-1 | P5 | M5.1 | ✔ D1.4.x – Training Program Launched (Phase 1: Awareness) | 2025-09-25 | 2025-09-25 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P6 | A6.1 | Define criteria for short-term success (training, integration, engagement) | 2026-02-01 | 2026-02-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P6 | A6.2 | Coordinate with pilot teams to collect success indicators (qualitative + quantitative) | 2026-02-04 | 2026-02-09 | 5 |  | Execution | Not Started | 0 | A6.1 | FS
WorkStream-1 | P6 | A6.3 | Document and publish pilot success stories (1 per BL) | 2026-02-07 | 2026-02-12 | 5 |  | Execution | Not Started | 0 | A6.2 | FS
WorkStream-1 | P6 | A6.4 | Update AIS Change Dashboard with early adoption metrics | 2026-02-10 | 2026-02-15 | 5 |  | Execution | Not Started | 0 | A6.3 | FS
WorkStream-1 | P6 | A6.5 | Distribute AIS success highlights via newsletter & CE briefing | 2026-02-13 | 2026-02-18 | 5 |  | Execution | Not Started | 0 | A6.4 | FS
WorkStream-1 | P6 | A6.6 | Host recognition moment for contributors from pilot BLs | 2026-02-16 | 2026-02-21 | 5 |  | Execution | Not Started | 0 | A6.5 | FS
WorkStream-1 | P6 | M6.1 | D1.3.x – Pilot Success Reports | 2026-02-19 | 2026-02-19 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P6 | M6.2 | D1.3.x – Change Adoption Dashboard (first version) | 2026-02-22 | 2026-02-22 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P7 | A7.1 | Analyze feedback and performance from pilots and early training phases | 2026-04-01 | 2026-04-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P7 | A7.2 | Refine and expand the CE AIS training program – Phase 2 (deep dive, BL-specific) | 2026-04-04 | 2026-04-09 | 5 |  | Execution | Not Started | 0 | A7.1 | FS
WorkStream-1 | P7 | A7.3 | Update Change Adoption Dashboard to reflect scalability targets | 2026-04-07 | 2026-04-12 | 5 |  | Execution | Not Started | 0 | A7.2 | FS
WorkStream-1 | P7 | A7.4 | Publish next AIS Transformation Newsletter with roadmap and wins | 2026-04-10 | 2026-04-10 | 0 |  | Milestone | Not Started | 0 | A7.3 | FS
WorkStream-1 | P7 | A7.5 | Expand coalition participation to include more operational leaders | 2026-04-13 | 2026-04-18 | 5 |  | Execution | Not Started | 0 | A7.4 | FS
WorkStream-1 | P7 | A7.6 | Host change review workshop to realign actions to D4.1 roadmap | 2026-04-16 | 2026-04-21 | 5 |  | Execution | Not Started | 0 | A7.5 | FS
WorkStream-1 | P7 | M7.1 | Submit D1.4.x – CE Training Program | 2026-04-19 | 2026-04-19 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P7 | M7.2 | Submit D1.3.x – Change Adoption Dashboard | 2026-04-22 | 2026-04-22 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P7 | M7.3 | Submit D1.3.x – Transformation Newsletter | 2026-04-25 | 2026-04-25 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P8 | A8.1 | Conduct lessons learned sessions with CE, D&T, and BL change agents | 2026-06-01 | 2026-06-06 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-1 | P8 | A8.2 | Update CE AIS governance plan with permanent roles and accountabilities | 2026-06-04 | 2026-06-09 | 5 |  | Execution | Not Started | 0 | A8.1 | FS
WorkStream-1 | P8 | A8.3 | Integrate AIS responsibilities into onboarding, job descriptions, and competency models | 2026-06-07 | 2026-06-12 | 5 |  | Execution | Not Started | 0 | A8.2 | FS
WorkStream-1 | P8 | A8.4 | Formalize AIS KPIs in CE/BL performance management and reporting cycles | 2026-06-10 | 2026-06-15 | 5 |  | Execution | Not Started | 0 | A8.3 | FS
WorkStream-1 | P8 | A8.5 | Publish AIS sustainability plan and long-term communication calendar | 2026-06-13 | 2026-06-13 | 0 |  | Milestone | Not Started | 0 | A8.4 | FS
WorkStream-1 | P8 | A8.6 | Submit final Workstream 1 Change Integration Report to CE | 2026-06-16 | 2026-06-16 | 0 |  | Milestone | Not Started | 0 | A8.5 | FS
WorkStream-1 | P8 | M8.1 | Final Handover of Change Management Artifacts (D1.1) | 2026-06-19 | 2026-06-19 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P8 | M8.2 | Final Handover of Communication Materials (D1.2 & D1.3.x) | 2026-06-22 | 2026-06-22 | 0 |  | Milestone | Not Started | 0
WorkStream-1 | P8 | M8.3 | Final Handover of Training Materials (D1.4.x) | 2026-06-25 | 2026-06-25 | 0 |  | Milestone | Not Started | 0
WorkStream-2 | P1 | GOV1 | Define AIS Governance Scope, Objectives, Alignment with SEC Strategy | 2025-05-20 | 2025-05-24 | 4 |  | Execution | Not Started | 0
WorkStream-2 | P1 | GOV2.1 | Identify Data Owners, Stewards, Custodians per Domain | 2025-05-23 | 2025-05-26 | 3 |  | Execution | Not Started | 0 | GOV1 | FS
WorkStream-2 | P1 | GOV2.2 | Draft RACI Matrix for Governance Roles | 2025-05-26 | 2025-05-28 | 2 |  | Execution | Not Started | 0 | GOV2.1 | FS
WorkStream-2 | P1 | GOV3 | Draft Data Governance Principles (Accountability, Transparency, Compliance) | 2025-05-29 | 2025-06-02 | 4 |  | Execution | Not Started | 0 | GOV2.2 | FS
WorkStream-2 | P1 | GOV4.1 | Define Asset Data Creation & Update Rules | 2025-06-01 | 2025-06-04 | 3 |  | Execution | Not Started | 0 | GOV3 | FS
WorkStream-2 | P1 | GOV4.2 | Define Asset Data Retention & Archiving Policies | 2025-06-04 | 2025-06-06 | 2 |  | Execution | Not Started | 0 | GOV4.1 | FS
WorkStream-2 | P1 | GOV5.1 | Classify Key Asset Data Elements (for AHI analytics) | 2025-06-07 | 2025-06-10 | 3 |  | Execution | Not Started | 0 | GOV4.2 | FS
WorkStream-2 | P1 | GOV5.2 | Define Data Quality Rules & Validation Logic | 2025-06-10 | 2025-06-13 | 3 |  | Execution | Not Started | 0 | GOV5.1 | FS
WorkStream-2 | P1 | GOV6.1 | Review Applicable Standards (IEC 61968, ISO 14224, IEC 81346) | 2025-06-13 | 2025-06-15 | 2 |  | Execution | Not Started | 0 | GOV5.2 | FS
WorkStream-2 | P1 | GOV6.2 | Map Standards to SEC AIS Use Cases | 2025-06-16 | 2025-06-18 | 2 |  | Execution | Not Started | 0 | GOV6.1 | FS
WorkStream-2 | P1 | GOV7 | Define Escalation Model and Exception Handling Process | 2025-06-19 | 2025-06-22 | 3 |  | Execution | Not Started | 0 | GOV6.2 | FS
WorkStream-2 | P1 | GOV8 | Define Governance KPIs and Monitoring Approach | 2025-06-22 | 2025-06-25 | 3 |  | Execution | Not Started | 0 | GOV7 | FS
WorkStream-2 | P1 | GOV9.1 | Draft Governance Rules for Modeling & Design Artifacts | 2025-06-25 | 2025-06-28 | 3 |  | Execution | Not Started | 0 | GOV8 | FS
WorkStream-2 | P1 | GOV9.2 | Review Modeling Governance with WS3 Leads | 2025-06-28 | 2025-06-30 | 2 |  | Execution | Not Started | 0 | GOV9.1 | FS
WorkStream-2 | P1 | GOV10 | Define Review and Approval Lifecycle for Data Models | 2025-07-01 | 2025-07-04 | 3 |  | Execution | Not Started | 0 | GOV9.2 | FS
WorkStream-2 | P1 | GOV11 | Define KPIs for Model Conformance and Completeness | 2025-07-04 | 2025-07-06 | 2 |  | Execution | Not Started | 0 | GOV10 | FS
WorkStream-2 | P1 | GOV12.1 | Conduct CE Governance Enablement Session | 2025-07-07 | 2025-07-09 | 2 |  | Execution | Not Started | 0 | GOV11 | FS
WorkStream-2 | P1 | GOV12.2 | Conduct BL Governance Workshop (Gx, Tx, Dx) | 2025-07-10 | 2025-07-12 | 2 |  | Execution | Not Started | 0 | GOV12.1 | FS
WorkStream-2 | P1 | GOV13 | Finalize & Submit AIS Implementation Governance Charter | 2025-07-13 | 2025-07-13 | 0 |  | Milestone | Not Started | 0 | GOV12.2 | FS
WorkStream-3 | P3 | WS3-P3-1 | Perform Data Profiling & Completeness Check | 2025-07-13 | 2025-07-18 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P3 | WS3-P3-2 | Evaluate Standardization vs. CE Model | 2025-07-17 | 2025-07-22 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P3 | WS3-P3-3 | Map Integration Points in Pilot Scope | 2025-07-21 | 2025-07-25 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P3 | WS3-P3-4 | Assess Governance & Ownership | 2025-07-25 | 2025-07-29 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P3 | WS3-P3-5 | Draft Scoped Operational Gap & Integration Report | 2025-07-29 | 2025-08-03 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P3 | WS3-P3-6 | Review with CE, D&T, and BL Stakeholders | 2025-08-02 | 2025-08-05 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P3 | WS3-P3-7 | Submit Final Operational Gap & Integration Report | 2025-08-06 | 2025-08-06 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P4 | WS3-P4-1 | Design Target Data Pipeline Architecture | 2025-08-12 | 2025-08-17 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P4 | WS3-P4-2 | Specify Integration Methods | 2025-08-16 | 2025-08-20 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P4 | WS3-P4-3 | Map Data Flow Across Critical Systems | 2025-08-20 | 2025-08-24 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P4 | WS3-P4-4 | Align Integration Design with Standards | 2025-08-24 | 2025-08-27 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P4 | WS3-P4-5 | Draft Integration Workflow Blueprint | 2025-08-28 | 2025-09-02 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P4 | WS3-P4-6 | Review with CE and Business Line Stakeholders | 2025-09-01 | 2025-09-04 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P4 | WS3-P4-7 | Submit Final Integration Workflow Blueprint | 2025-09-05 | 2025-09-05 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P5 | WS3-P5-1 | Consolidate Requirements and Integration Blueprint | 2025-08-28 | 2025-09-01 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P5 | WS3-P5-2 | Define Execution Roadmap and Milestones | 2025-09-01 | 2025-09-04 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P5 | WS3-P5-3 | Identify Pilot-Specific Risks and Mitigation Plans | 2025-09-05 | 2025-09-08 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P5 | WS3-P5-4 | Assign Roles, Responsibilities, and KPIs | 2025-09-09 | 2025-09-12 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P5 | WS3-P5-5 | Conduct Execution Readiness Review | 2025-09-13 | 2025-09-16 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P5 | WS3-P5-6 | Submit Final Pilot Execution Plan Package | 2025-09-17 | 2025-09-17 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-1 | Identify Key Data Sources and AHI Attributes | 2025-09-01 | 2025-09-05 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-2 | Conduct Data Profiling for Completeness & Consistency | 2025-09-05 | 2025-09-10 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-3 | Document Metadata (Source, Frequency, Ownership) | 2025-09-09 | 2025-09-13 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-4 | Align with Standards (IEC 61968/70, ISO 14224) | 2025-09-13 | 2025-09-16 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-5 | Develop Metadata Catalog and Profiling Report | 2025-09-17 | 2025-09-21 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-6 | Review Catalog and Report with CE & BL Teams | 2025-09-21 | 2025-09-24 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-7 | Submit Final Data Catalog Report | 2025-09-25 | 2025-09-25 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-8 | Review Existing BL Data Models (Attributes, Relationships) | 2025-09-23 | 2025-09-27 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-9 | Compare Against Industry Standards (IEC, ISO, CIM) | 2025-09-27 | 2025-10-01 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-10 | Identify Unification Opportunities & Gaps | 2025-10-01 | 2025-10-04 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-11 | Develop Unified Logical Data Model (UML) | 2025-10-05 | 2025-10-10 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-12 | Validate with Business Line SMEs | 2025-10-09 | 2025-10-12 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-13 | Refine and Finalize UML Diagram | 2025-10-13 | 2025-10-16 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-14 | Submit CE-BL Unified Model (UML Diagram) | 2025-10-17 | 2025-10-17 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-15 | Define Schemas for Data-in-Motion and Data-at-Rest | 2025-10-13 | 2025-10-17 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-16 | Select Interoperability Formats (JSON, XML, RDF) | 2025-10-17 | 2025-10-20 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-17 | Design Physical Database Schema | 2025-10-21 | 2025-10-26 | 5 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-18 | Generate DDL Scripts for Implementation | 2025-10-25 | 2025-10-28 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-19 | Map Source Attributes to Unified Model | 2025-10-29 | 2025-11-02 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-20 | Configure ETL/Streaming Workflows | 2025-11-02 | 2025-11-06 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-21 | Submit Physical Schema & Mapping Package | 2025-11-06 | 2025-11-06 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-22 | Coordinate Environment Setup with Digital Team | 2025-11-03 | 2025-11-06 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-23 | Configure Push-Pull API and Data Pipelines | 2025-11-06 | 2025-11-10 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-24 | Validate Integration with Sample Data | 2025-11-09 | 2025-11-12 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-25 | Review Demo with CE and Business Line Teams | 2025-11-12 | 2025-11-15 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P6 | WS3-P6-26 | Submit Push-Pull Integration Validation Report | 2025-11-15 | 2025-11-15 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-1 | Evaluate Governance Framework Adoption | 2025-12-01 | 2025-12-05 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-2 | Assess Business Line Competencies and Gaps | 2025-12-05 | 2025-12-08 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-3 | Propose Additional Governance Structures or Roles | 2025-12-09 | 2025-12-12 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-4 | Submit AIS Scalability Report | 2025-12-13 | 2025-12-13 | 0 |  | Milestone | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-5 | Evaluate Existing AIS Architecture for Scalability | 2025-12-17 | 2025-12-21 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-6 | Collaborate on Modular Architecture Enhancements | 2025-12-21 | 2025-12-25 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-7 | Define Interoperability Strategy and Integration Points | 2025-12-25 | 2025-12-29 | 4 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-8 | Propose Phased Rollout Plan and Prioritization | 2025-12-29 | 2026-01-01 | 3 |  | Execution | Not Started | 0 |  | FS
WorkStream-3 | P7 | WS3-P7-9 | Submit Final Data Architecture Blueprint & Roadmap | 2026-01-02 | 2026-01-02 | 0 |  | Milestone | Not Started | 0 |  | FS

## Risk_Register
Risk ID | Workstream | Activity Code | Activity Name | Risk Description | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Mitigation Plan | Contingency Plan | Owner | Status | Target Resolution Date | Last Updated | Comments
R-001 | WS2 | Governance Charter | Lack of clear data ownership across business lines | Governance | 4 | 4 | 16 | High | Define and agree on data ownership roles with CE and business lines early in the project | Escalate unclear ownership cases to the steering committee for resolution | Data Governance Lead | Open | 2025-06-15 | 2025-05-01
R-002 | WS2 | Governance Charter | Weak data stewardship practices or untrained stewards | Governance | 3 | 3 | 9 | Medium | Deliver training and onboarding for data stewards as part of Change Management | Assign temporary stewards from CE for critical activities | Change Management Lead | Open | 2025-07-01 | 2025-05-01
R-003 | WS3 | Data Profiling | Unidentified data quality issues in legacy systems | Data Quality | 4 | 4 | 16 | High | Start profiling early and prioritize critical asset classes | Scope additional cleansing activities and extend profiling effort if needed | Data Profiling Lead | Open | 2025-08-01 | 2025-05-01
R-004 | WS3 | Data Profiling | Inadequate cleansing and validation tools | Tooling | 3 | 4 | 12 | High | Evaluate profiling toolkits in month 2 and procure early | Use custom scripts and manual validation where needed | IT Integration Lead | Open | 2025-07-15 | 2025-05-01
R-005 | WS2 | Integration Blueprint | OT/IT system incompatibility or protocol mismatch | Integration | 4 | 4 | 16 | High | Validate interfaces and protocol compatibility in the design phase | Introduce middleware solutions to enable translation | Integration Architect | Open | 2025-07-30 | 2025-05-01
R-006 | WS3 | Push-Pull Integration | Lack of real-time integration capability | Integration | 3 | 4 | 12 | High | Define push/pull architecture and run a pilot with sample data | Use batch processing or partial real-time updates where needed | Systems Engineer | Open | 2025-09-01 | 2025-05-01
R-007 | WS3 | Model Customization | Incorrect or incomplete semantic model mapping | Modeling | 3 | 5 | 15 | High | Review mappings with CE and validate against IEC CIM | Allow rework cycles with change control | Data Architect | Open | 2025-10-01 | 2025-05-01
R-008 | WS3 | Scalability Planning | Scalability of pilot results not guaranteed | Deployment | 3 | 4 | 12 | High | Capture scalability indicators during PoC and standardize templates | Plan redesign activities post-pilot with sufficient buffer | Pilot Coordinator | Open | 2026-01-30 | 2025-05-01
R-009 | WS2 | Change Management | Business resistance to new roles and responsibilities | Organizational | 3 | 4 | 12 | High | Engage stakeholders early and reinforce role clarity in communications | Adjust role assignments and introduce change champions | Change Lead | Open | 2025-07-01 | 2025-05-01
R-010 | WS2 | Communication Strategy | Communication plan is not effectively executed | Change Management | 2 | 4 | 8 | Medium | Define message cadence and use multi-channel engagement | Trigger intensive sessions or campaign relaunch | Comms Lead | Open | 2025-06-30 | 2025-05-01
R-011 | WS2 | Staffing & Delivery | Limited availability of skilled consultants or SMEs | Resourcing | 4 | 4 | 16 | High | Pre-confirm availability and assign backups in contract | Use external support or adjust timeline milestones | PMO | Open | 2025-06-01 | 2025-05-01
R-012 | WS3 | Tooling & Profiling | Tooling limitations for data profiling or integration | Technology | 3 | 4 | 12 | High | Assess tool requirements early and secure access in Phase 1 | Implement Python/Excel workarounds or explore open-source tools | Tech Lead | Open | 2025-07-15 | 2025-05-01

## Issue_Tracker
Issue ID | Workstream | Activity Name | Issue Description | Reported By | Assigned To | Date Reported | Severity | Impact Area | Root Cause | Resolution Plan | Target Resolution Date | Status | Actual Resolution Date | Escalated (Yes/No) | Comments / Updates

## References
Person Name | Role | WorkStreams | Phases | Task Types | Activity Status | Dependency Types
Lavjit Singh | Project Director | WorkStream-1 | P1 | Execution | Not Started | FS
Adel Gamal | Project Manager | WorkStream-2 | P2 | Planning | In Progress | SS
Don Sunny | Senior Consultant | WorkStream-3 | P3 | Milestone | Completed | FF
Ganesh Shinde | Consultant |  | P4 | Continuous | Delayed | SF
Samuel Ezannaya | Consultant |  | P5 | Approval | On Hold
Stefan Stroobants | Modeling Expert |  | P6 |  | Cancelled
Jaco Roesch | Modeling Expert |  | P7
Gustav Brand | Data Archiect |  | P8
External Consultant | Modeling Expert
Seyed Khali | Change Mgmt Expert